## Current
Data Science Capstone Project Submission due on 25 April
Release | Iteration | Backlog item # | Backlog item | Task Id | Task | Status
1 | 2016-04-02 | B1 | Bring application to work, minimum viable product
1 | 2016-04-02 |  |  | 1 | Create app ("Hello words") and publish to shinyapps | Done
1 | 2016-04-02 |  |  | 2 | Extend UI: Textbox, suggestion line, submit button, help text | Done
1 | 2016-04-02 |  |  | 4 | Modify predict function: predictWord( phrase, n: number of Suggestions to return) return a data frame with n suggestions | Done
1 | 2016-04-02 |  |  | 5 | Extend Server: Read files, process after submit | Done
1 | 2016-04-02 |  |  | 6 | remove rownames | Done
1 | 2016-04-02 |  |  | 7 | omit 1 time ngrams or limit the number of ngrams for each type, eg. 10000 unigrams, 100000 bigrams,… | Done
1 | 2016-04-04 |  |  | 8 | Move/Merge code to Github | Done
1 | 2016-04-04 |  |  | 9 | Review/ modify export and import of ngrams for app | Done
1 | 2016-04-05 |  |  | 10 | make common functions for cleansing etc. | Ready
Release 1: 6.4.2016 | ======================= | ======================= | ======================= |  | =======================
2 |  | B2a | Prediction: Define sizes for Corpus(Training and Test set) and ngrams
2
2 |  | B2 | Check prediction: Define and run test set
2
2 |  | B3 | Improve app: Check resource usage, monitoring, uptime
2
2 |  | B4 | Presentation: Draft
Release 2: 8.4.2016 | ======================= | ======================= | ======================= |  | =======================
3 |  | B5 | Smoothing: Kneser-Ney
3
3 |  | B6 | Improve prediction and app: Casing
3
3 |  | B7 | Presentation: Review
Release 3: 12.4.2016 | ======================= | ======================= | ======================= |  | =======================
4 |  | B8 | Improve App: React on keystrokes
4
4 |  | B9 | Improve prediction: word competion
4
4 |  | B10 | Presentation: Review
Release 4: 15.4.2016 | ======================= | ======================= | ======================= |  | =======================
5 |  | B11 | Improve prediction: clustering
5
5 |  | B12 | Presentation: Review
Release 5: 20.4.2016 | ======================= | ======================= | ======================= |  | =======================
6 |  | B13 | App final
6
6 |  | B13 | Presentation: Final
Relase 6: 23.4.2016 | ======================= | ======================= | ======================= |  | =======================

## Original
Data Science Capstone Project Submission due on 25 April
Release | Iteration | Backlog item # | Backlog item | Task Id | Task
1 | 2016-04-02 | B1 | Bring application to work, minimum viable product
1 | 2016-04-02 |  |  | 1 | Create app ("Hello words") and publish to shinyapps
1 | 2016-04-02 |  |  | 2 | Extend UI: Textbox, suggestion line, submit button, help text
1 | 2016-04-02 |  |  | 4 | Modify predict function: predictWord( phrase, n: number of Suggestions to return) return a data frame with n suggestions
1 | 2016-04-02 |  |  | 5 | Extend Server: Read files, process after submit
| 2016-04-02 |  |  | 3 | Corpus 1%
1 | 2016-04-02 |  |  | 6 | remove rownames
1 | 2016-04-02 |  |  | 7 | omit 1 time ngrams or limit the number of ngrams for each type, eg. 10000 unigrams, 100000 bigrams,…
1 | 2016-04-04 |  |  | 8 | Move/Merge code to Github
1 | 2016-04-04 |  |  | 9 | Review/ modify export and import of ngrams for app
1 | 2016-04-05 |  |  | 10 | make common functions for cleansing etc.
Release 1: 6.4.2016 | ======================= | ======================= | ======================= |  | =======================
2 |  | B2a | Prediction: Define sizes for Corpus(Training and Test set) and ngrams
2
2 |  | B2 | Check prediction: Define and run test set
2
2 |  | B3 | Improve app: Check resource usage, monitoring, uptime
2
2 |  | B4 | Presentation: Draft
Release 2: 8.4.2016 | ======================= | ======================= | ======================= |  | =======================
3 |  | B5 | Smoothing: Kneser-Ney
3
3 |  | B6 | Improve prediction and app: Casing
3
3 |  | B7 | Presentation: Review
Release 3: 12.4.2016 | ======================= | ======================= | ======================= |  | =======================
4 |  | B8 | Improve App: React on keystrokes
4
4 |  | B9 | Improve prediction: word competion
4
4 |  | B10 | Presentation: Review
Release 4: 15.4.2016 | ======================= | ======================= | ======================= |  | =======================
5 |  | B11 | Improve prediction: clustering
5
5 |  | B12 | Presentation: Review
Release 5: 20.4.2016 | ======================= | ======================= | ======================= |  | =======================
6 |  | B13 | App final
6
6 |  | B13 | Presentation: Final
Relase 6: 23.4.2016 | ======================= | ======================= | ======================= |  | =======================