## Current
Data Science Capstone Project Submission due on 25 April
Release | Iteration | Backlog item # | Backlog item | Task Id | Task | Status
1 | 2016-04-02 | B1 | Bring application to work, minimum viable product
1 | 2016-04-02 |  |  | 1 | Create app ("Hello words") and publish to shinyapps | Done
1 | 2016-04-02 |  |  | 2 | Extend UI: Textbox, suggestion line, submit button, help text | Done
1 | 2016-04-02 |  |  | 4 | Modify predict function: predictWord( phrase, n: number of Suggestions to return) return a data frame with n suggestions | Done
1 | 2016-04-02 |  |  | 5 | Extend Server: Read files, process after submit | Done
1 | 2016-04-02 |  |  | 6 | remove rownames | Done
1 | 2016-04-02 |  |  | 7 | omit 1 time ngrams or limit the number of ngrams for each type, eg. 10000 unigrams, 100000 bigrams,… | Done
1 | 2016-04-04 |  |  | 8 | Move/Merge code to Github | Done
1 | 2016-04-04 |  |  | 9 | Review/ modify export and import of ngrams for app | Done
1 | 2016-04-05 |  |  | 10 | make common functions for cleansing etc. | Done
1 | 2016-04-07 |  |  | 11 | Deploy to shinyapps | Done
Release 1: 8.4.2016 | ======================= | ======================= | ======================= |  | =======================
|  | B2a | Prediction: Define sizes for Corpus(Training and Test set) and ngrams
|  |  |  | 1 | Based on computing capacity define a percentage of the corpus for training and test set | Done
2 |  |  |  | 2 | Based on the outcome of the above and based response time requirements define a size (number of entries for 1,2 and3-grams | Done
|  |  |  | 3 | Define and measure response time of the predict funciton | Done
|  |  |  | 4 | Deploy to shinyapps | Done
2 |  | B2 | Check prediction: Define and run test set
|  |  |  | 1 | With a given percentage of the test set define a function that can read the test set line by line | Done
|  |  |  | 2 | Perform cleansing on test set | Done
|  |  |  | 3 | Define a funtion that extracts blank limited substings with next word out of a line | Done
|  |  |  | 4 | Define a funtion that extracts blank limited substings of a line | Done
|  |  |  | 5 | Build something to run tests with the predict fuction | Done
2 |  |  |  | 6 | Have some measure of results (% of correct predicitons) | Done
2 |  | B3 | Improve app: Check resource usage, monitoring, uptime
|  |  |  | 1 | Measure response time and memory consumtion on the test server | Done
2 |  |  |  | 2 | review and consolidate common function | Done
|  |  |  | 3 | Improve memory usage and response time
2 |  | B8 | Improve App: React on keystrokes
1
Release 2: 16.4.2016 | ======================= | ======================= | ======================= |  | =======================
3 |  | B5 | Smoothing: Kneser-Ney |  | More or less… | Done
3
3 |  | B4 | Presentation: Draft
2 | [5 empty] | Done
Release 3: 17.4.2016 | ======================= | ======================= | ======================= |  | =======================
4
4 |  | B9 | Improve prediction: word completion |  |  | Obsolete
3 |  | B6 | Improve prediction and app: Casing |  |  | Obsolete
4
4 |  | B10 | Presentation: 80 %
4 |  | B11 | Improve Processing |  | Make up mind about percentages and variants to run | Done
[5 empty] | define sizes | Done
[5 empty] | commonProcessing.R | Done
[5 empty] | adapt paths and file names | In Progress
[5 empty] | Have one preprocessing | Done
Optimize prediciton with hash
Build hash table with concatenated string
use hash table for prediction with concatenated (and split) string
Define and run testsuite
(re)define tests (Base, KN, full)
implement store results for each run
4 |  | B10 | Presentation: Ready for submission
Release 4: 20.4.2016 | ======================= | ======================= | ======================= |  | =======================
4 |  | B10 | Presentation: Ready for submission
5 |  | B11 | Improve prediction: clustering
5
6 |  | B13 | App final
6
6 |  | B13 | Presentation: Final
Relase 6: 23.4.2016 | ======================= | ======================= | ======================= |  | =======================

## Original
Data Science Capstone Project Submission due on 25 April
Release | Iteration | Backlog item # | Backlog item | Task Id | Task
1 | 2016-04-02 | B1 | Bring application to work, minimum viable product
1 | 2016-04-02 |  |  | 1 | Create app ("Hello words") and publish to shinyapps
1 | 2016-04-02 |  |  | 2 | Extend UI: Textbox, suggestion line, submit button, help text
1 | 2016-04-02 |  |  | 4 | Modify predict function: predictWord( phrase, n: number of Suggestions to return) return a data frame with n suggestions
1 | 2016-04-02 |  |  | 5 | Extend Server: Read files, process after submit
| 2016-04-02 |  |  | 3 | Corpus 1%
1 | 2016-04-02 |  |  | 6 | remove rownames
1 | 2016-04-02 |  |  | 7 | omit 1 time ngrams or limit the number of ngrams for each type, eg. 10000 unigrams, 100000 bigrams,…
1 | 2016-04-04 |  |  | 8 | Move/Merge code to Github
1 | 2016-04-04 |  |  | 9 | Review/ modify export and import of ngrams for app
1 | 2016-04-05 |  |  | 10 | make common functions for cleansing etc.
Release 1: 6.4.2016 | ======================= | ======================= | ======================= |  | =======================
2 |  | B2a | Prediction: Define sizes for Corpus(Training and Test set) and ngrams
2
2 |  | B2 | Check prediction: Define and run test set
2
2 |  | B3 | Improve app: Check resource usage, monitoring, uptime
2
2 |  | B4 | Presentation: Draft
Release 2: 8.4.2016 | ======================= | ======================= | ======================= |  | =======================
3 |  | B5 | Smoothing: Kneser-Ney
3
3 |  | B6 | Improve prediction and app: Casing
3
3 |  | B7 | Presentation: Review
Release 3: 12.4.2016 | ======================= | ======================= | ======================= |  | =======================
4 |  | B8 | Improve App: React on keystrokes
4
4 |  | B9 | Improve prediction: word competion
4
4 |  | B10 | Presentation: Review
Release 4: 15.4.2016 | ======================= | ======================= | ======================= |  | =======================
5 |  | B11 | Improve prediction: clustering
5
5 |  | B12 | Presentation: Review
Release 5: 20.4.2016 | ======================= | ======================= | ======================= |  | =======================
6 |  | B13 | App final
6
6 |  | B13 | Presentation: Final
Relase 6: 23.4.2016 | ======================= | ======================= | ======================= |  | =======================